## OpenJDK Migration Project Plan
OpenJDK Migration Project Plan
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.2 | Project Scope |  |  |  |  | 0%
1.3 | Success Criteria |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Build Project Team (i.e., focus team) |  |  |  |  | 0%
Timeline
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Communication Plan |  |  |  |  | 0%
2.2 | Risk Management Plan
2.3 | Create Project Repository |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
4 | Discover
4.1 | Inventory the Java estate |  |  |  |  | 0%
4.2 | Classify Installation Paths |  |  |  |  | 0%
4.3 | Identify and document Application Owners and environment custodians |  |  |  |  | 0%
4.4 | Identify and document specific product SMEs |  |  |  |  | 0%
4.5 | Conduct Application Interviews |  |  |  |  | 0%
4.6 | Run discovery tools (SAM, File System Crawlers, etc.) |  |  |  |  | 0%
4.7 | Classify application and product details |  |  |  |  | 0%
4.8 | Identify and document specific product SMEs |  |  |  |  | 0%
4.9 | Prepare the bucket classification. |  |  |  |  | 0%
4.10 | Make sure all license products have actual licenses |  |  |  |  | 0%
4.11 | Create a playbook for each bucket |  |  |  |  | 0%
5 | Execution
5.1 | Execution - three stage process - Quick switch, commit changes, Java runtime removal |  |  |  |  | 0%
5.1 | Run internal audits |  |  |  |  | 0%
6 | Validation
6.1 | Validation and ergonomic test strategy |  |  |  |  | 0%
6.2 | Stabilization phase |  |  |  |  | 0%